## Sheet1
Week | Satinder Singh | Atamjeet Singh | Arzaan Singh | Corey Singh
2016-09-04 | • reached out to peers to form group
2016-09-11 | • reseached project ideas • formed slack channel for group communication • github account • deliverable 0 submitted
2016-09-18 | • decided on tutorTonight app • discussed architecture • explored requirements and flow of app using diagrams on slack • split up tasks for Deliverable 1
2016-09-25 | • completed first page for D1 • designed logo • worked on slides for presentation | • completed optional mock up diagram/video for D1 • worked on slides for presentation | • completed functional portions for D1 • worked on slides for presentation | • completed non-functional for D1 • worked on slides for presentation
2016-10-02 | • created an Amazon Web Services Mobile Hub for hosting/back end • researched all available services on AWS to decided what to include (Lambda, DynamoDB, Cognito, IAM, API Gateway, SNS, CloudFront) • designed database logic
2016-10-09 | • experiment with Xcode and Swift | • experiment with Lambda for back-end logic | • experiment with Cognito for sign-up/sign-in services | • learn about Swift for UI
2016-10-16 | • experiment with Xcode and Swift | • experiment with Lambda for back-end logic | • experiment with Cognito for sign-up/sign-in services | • learn about Swift for UI
2016-10-23 | • Worked on UI (SignIn, Teach, Settings) | • Worked on the database, fixing errors | • Worked on UI (Home, Learn) Created prototypes and statically populated names. | • Worked on UI communicating with the database
2016-10-30 | • Worked on UI (SignIn, Teach, Settings) | • Worked on the database, fixing errors | • Worked on UI (Home, Learn) Created prototypes and statically populated names. | • Worked on UI communicating with the database
2016-11-06 | • Worked on UI (SignIn, Teach, Settings) | • Worked on the database, fixing errors | • Worked on UI (Home, Learn) Created prototypes and statically populated names. | • Worked on UI communicating with the database
2016-11-12 | • Worked on UI (SignIn, Teach, Settings) • Sign in, sign up all works with databases , fixed navigation bars, got global variables to work | • Worked on the database, made various functions. Also fixed errors | • Worked on UI (Home, Learn) Created prototypes and statically populated names. | • Worked on the report • Worked on UI communicated with the database • Figured out how to code the transition of screens rather than using the Interface Builder
2016-11-13 | • Worked on UI (SignIn, Teach, Settings) • Worked on making the UI dyanmic • Worked on populating courses in the search bar | • Worked on the database, made various functions. Also fixed errors | • Worked on UI (Home, Learn) Created prototypes and statically populated names. • Worked on making the UI dyanmic • Worked on populating courses in the search bar | • Worked on the report • Worked on UI communicated with the database • Figured out how to code the transition of screens rather than using the Interface Builder
2016-11-14 | • Worked on UI (SignIn, Teach, Settings) • Worked on making the UI dyanmic • Worked on populating courses in the search bar | • Worked on the database, made various functions. Also fixed errors | • Worked on UI (Home, Learn) • Worked on making the UI dyanmic • Worked on populating courses in the search bar | • Worked on UI communicated with the database • Figured out how to code the transition of screens rather than using the Interface Builder
2016-11-16
2016-11-17 | • Finalized the App for presentation | • Finalized the App for presentation and changed the UI | • Finalized the App for presentation | • Finalized the App for presentation
2016-11-19 | • learnt how to colour pages properly and worked on prototyping for the HomeViewController | - | - | • updated the SignInViewController to create Students as well as Users
2016-11-22 | • Discusses the things remaining to work on | • Discusses the things remaining to work on | • Discusses the things remaining to work on | • Discusses the things remaining to work on
Keyboard shortcutsl (mac)
| new line within cell | opt+cmd+enter
| bullet point | opt+8
Formulas:
Week = [Week, row above]+7